## Slide 1: Business Case Development
Making a Compelling Case
By: Beverly Primeau MBA-RN

## Slide 2: Objectives
Attendees will:
  Learn the components of a business case
  Learn to make a compelling argument
  What leadership needs to know before decisions are made
  Opportunity for Q&A

## Slide 3: Executive Summary
Opportunity/ Problem Statement
Project Scope
Alignment with organizations goals and objectives
Project Support / Key Stakeholders
Alternative Solutions Evaluated
Key Project Assumptions
Cost Summary
    Capital and Operating

## Slide 4: Market Analysis
What need does this service/plan meet
How does the project/opportunity improve upon existing services
What is the target market (geography) for this service/project
Identify competitors (that are involved with this project)
Does this service provide a competitive advantage.
Is there an immediate competitive threat to mitigate
Will this service/project outcome compete with any existing services or departments
What is the market demand for the proposed project

## Slide 5: Project Operations
What is the current location of this program/service/technology described in this business case
Does the new proposal involve a new location, expansion of current location or closing of location?
Will this proposal impact the operations of another service or program?
Will the current management structure be affected by this project?
What are current volumes and recent volume trends
What are current quality metrics and scores? Do you anticipate the project will impact these scores?
How will you measure if this program is operated efficiently?
What other program investments/changes have been made over the last 5 years
Will this project require a marketing campaign?

## Slide 6: Project Operations Continued:
Staffing
  Current workforce
  Total new hires needed by position type
Are there any recruitment/ “hard to fill” positions required for the success of this project?
Are there any training or licensing requirements that will be needed

## Slide 7: Financial Needs
Current Operating Margin
Current Contribution Margin
Does this project require a capital investment
What is the program payer mix (revenue stream)
What is the payment model for this program (FFS, Risk/Value, Self-Pay)
Will this project result in a reimbursable service
Is there a potential community benefit
Does this proposed program have the ability to be profitable
Is there an anticipated ROI
Is there an anticipated operating margin

## Slide 8: Detailed Project Costs
Capital Investments
Staff
Purchased Services (non-payroll labor)
Information Technology (annual maintenance and support)
Supplies
Service Contracts
Maintenance
Relocation Expense
Lease Costs
Marketing
Depreciation

## Slide 9: Pro-forma
Definition: A statement showing potential or expected income, costs, assets, or liabilities, especially in relation to some planned or expected act or situation. ~ Oxford Dictionary~
Usually projects multi-year to determine ROI timeframe.

## Slide 10: Regulatory Requirements
Licensing Boards
CMS
DHHS
NH Health Facilities Administration
Accreditation Agency
Other

## Slide 11: Project Execution Needs
Timeline
  Proposed Start Date
  Estimated Completion Date
  Is there an urgent need for this project to execute and implement
Project Risks/Barriers
  Describe any events that would prevent the completion of this project.

## Slide 12: Questions?